## Sheet1
Machine Bottleneck
|  |  |  | Weight | Obj.
Last Finish |  |  | 30 | 1 | 30
Maximum Past Due |  |  | 8 | 1 | 8
Total of Past Dues |  |  | 0 | 1 | 28
Objective to Minimize |  |  |  |  | 66
Job Table
Job | Release | Duration | Due | Start | Finish | Finish-Due | Early | Late | Late-Early
A | 2 | 5 | 10 | 5 | 10 | 0 | 0 | 0 | 0
B | 5 | 6 | 21 | 15 | 21 | 0 | 0 | 0 | 0
C | 4 | 8 | 15 | 7 | 15 | 0 | 0 | 0 | 0
D | 0 | 4 | 10 | 6 | 10 | 0 | 0 | 0 | 0
E | 0 | 2 | 5 | 3 | 5 | 0 | 0 | 0 | 0
F | 8 | 3 | 15 | 12 | 15 | 0 | 0 | 0 | 0
G | 9 | 2 | 22 | 20 | 22 | 0 | 0 | 0 | 0
Disjunctive Ordering Constraints
BigM | 100
|  |  | I finishes before J starts |  | J finishes before I starts
Job I | Job J | I before J | Finish i | Start j |  |  | Finish j | Start i
A | B | 0 | 7 | 22 | 122 |  | 28 | 2 | 2
A | C | 0 | 7 | 11 | 111 |  | 19 | 2 | 2
A | D | 0 | 7 | 7 | 107 |  | 11 | 2 | 2
A | E | 0 | 7 | 0 | 100 |  | 2 | 2 | 2
A | F | 0 | 7 | 19 | 119 |  | 22 | 2 | 2
A | G | 0 | 7 | 28 | 128 |  | 30 | 2 | 2
B | C | 0 | 28 | 11 | 111 |  | 19 | 22 | 22
B | D | 0 | 28 | 7 | 107 |  | 11 | 22 | 22
B | E | 0 | 28 | 0 | 100 |  | 2 | 22 | 22
B | F | 0 | 28 | 19 | 119 |  | 22 | 22 | 22
B | G | 0 | 28 | 28 | 128 |  | 30 | 22 | 22
C | D | 0 | 19 | 7 | 107 |  | 11 | 11 | 11
C | E | 0 | 19 | 0 | 100 |  | 2 | 11 | 11
C | F | 0 | 19 | 19 | 119 |  | 22 | 11 | 11
C | G | 0 | 19 | 28 | 128 |  | 30 | 11 | 11
D | E | 0 | 11 | 0 | 100 |  | 2 | 7 | 7
D | F | 0 | 11 | 19 | 119 |  | 22 | 7 | 7
D | G | 0 | 11 | 28 | 128 |  | 30 | 7 | 7
E | F | 0 | 2 | 19 | 119 |  | 22 | 0 | 0
E | G | 0 | 2 | 28 | 128 |  | 30 | 0 | 0
F | G | 0 | 22 | 28 | 128 |  | 30 | 19 | 19